## Sign Up
Product Name |  | InsureCow | TC Start Date | 2024-01-21 | TC Execution Start Date |  |  |  |  | TEST CASE
Module Name |  | Sign Up and Sign In | TC End Date |  | TC Execution End Date |  |  |  |  | PASS | 12
Epic |  |  | Test Case Developed By | Md. Sakhawat Hossain Rabbi | Browser (tested) | Yes |  |  |  | FAIL | 0
Developer Name (TL) |  |  | Test Case Reviewed By | Tahmid Ferdous | [5 empty] | Not Executed | 0
Test Executed by | [9 empty] | Out of Scope | 0
[10 empty] | TOTAL | 12
SL NO. | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status
1 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Chrome | 1. Goto different browsers 2. Search 'InsureCow' 3. Goto the website |  |  | Passed
2 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Mozilla Firefox | 1. Goto different browsers 2. Search 'InsureCow' 3. Goto the website |  |  | Passed
3 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Microsoft Edge | 1. Goto different browsers 2. Search 'InsureCow' 3. Goto the website |  |  | Passed
4 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Opera Mini | 1. Goto different browsers 2. Search 'InsureCow' 3. Goto the website |  |  | Passed
2 | User Management | UI Testing | Sign Up | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/login 2. Click on Register button at the right corner 3. Check the spelling and grammar of the website |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/login 2. Click on Register button at the right corner 3. Check the font, text color and style |  |  | Passed
4 |  |  |  | Verifying mandatory field is marked with a red asterisk | Red asterisk should be present | Not Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/login 2. Check red asterisk beside mandatory field |  |  | Passed
5 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/login 2. Hover over every fields |  |  | Passed
6 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/login 2. Click on Register button at the right corner 3. Check alignment of the fields |  |  | Passed
7 |  |  |  | Checkbox beside 'Sign Up' | Checkbox should be present | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/login 2. Check checkbox beside 'Sign Up for Newsletter' |  |  | Passed
8 |  |  |  | Checkbox beside 'Remember Me' | Checkbox should be present | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/login 2. Click on Register button at the right corner 3. Check checkbox beside 'Remember Me' |  |  | Passed
9 |  |  |  | Checkbox beside 'Forgot Password' | Checkbox should be present | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/login 2. Click on Register button at the right corner 3. Check 'Remember Me' checkbox |  |  | Passed
|  |  |  | Improvement Scopes | 1. Password should be defined as Strong, Medium, High 2. Show red mark below password(While give wrong password)

## Super Admin Panel
Product Name |  | InsureCow | TC Start Date | 2023-11-09 | TC Execution Start Date |  |  |  |  | TEST CASE
Module Name |  | Super Admin Panel | TC End Date |  | TC Execution End Date |  |  |  |  | PASS | 8
Epic |  |  | Test Case Developed By | Md. Sakhawat Hossain Rabbi | Browser (tested) | Yes |  |  |  | FAIL | 0
Developer Name (TL) |  |  | Test Case Reviewed By | Tahmid Ferdous | [5 empty] | Not Executed | 0
Test Executed by | [9 empty] | Out of Scope | 0
[10 empty] | TOTAL | 8
SL NO. | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status
1 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Chrome | 1. Goto different browsers 2. Search 'InsureCow' 3. Goto the website |  |  | Passed
2 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Mozilla Firefox | 1. Goto different browsers 2. Search 'InsureCow' 3. Goto the website |  |  | Passed
3 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Microsoft Edge | 1. Goto different browsers 2. Search 'InsureCow' 3. Goto the website |  |  | Passed
4 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Opera Mini | 1. Goto different browsers 2. Search 'InsureCow' 3. Goto the website |  |  | Passed
2 | User Management | UI Testing | Super Admin Panel | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Check the spelling and grammar of the website |  |  | Passed
3 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Check the font, text color and style |  |  | Passed
5 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Hover over every fields |  |  | Passed
6 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Check alignment of the fields |  |  | Passed
|  |  |  | Improvement Scopes | 1. Message box should edit

## Dashboard
Product Name |  | InsureCow | TC Start Date | 11/12/2023 11/13/2023 | TC Execution Start Date |  |  |  |  | TEST CASE
Module Name |  | Dashboard | TC End Date |  | TC Execution End Date |  |  |  |  | PASS | 46
Epic |  |  | Test Case Developed By | Md. Sakhawat Hossain Rabbi | Browser (tested) | Yes |  |  |  | FAIL | 12
Developer Name (TL) |  |  | Test Case Reviewed By | Tahmid Ferdous | [5 empty] | Not Executed | 0
Test Executed by | [9 empty] | Out of Scope | 0
[10 empty] | TOTAL | 58
SL NO. | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status
1 |  | Browser Compatibility Testing | Brouser Test | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Chrome | 1. Goto different browsers 2. Search 'InsureCow' 3. Goto the website |  |  | Passed
2 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Mozilla Firefox | 1. Goto different browsers 2. Search 'InsureCow' 3. Goto the website |  |  | Passed
3 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Microsoft Edge | 1. Goto different browsers 2. Search 'InsureCow' 3. Goto the website |  |  | Passed
4 |  | Browser Compatibility Testing |  | Checking by running the site in different browsers | Should run in different browsers | Found as per expectation | Opera Mini | 1. Goto different browsers 2. Search 'InsureCow' 3. Goto the website |  |  | Passed
1 | Admin Panel | UI Testing | Dashboard | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/company/dashboard 2. Check the spelling and grammar of the website |  |  | Passed
2 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/company/dashboard 2. Check the spelling and grammar of the website |  |  | Passed
3 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/company/dashboard 2. Check the spelling and grammar of the website |  |  | Passed
4 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/company/dashboard 2. Check the spelling and grammar of the website |  |  | Passed
Number Of Companies
1 | Admin Panel | UI Testing | Numbers Of Companies | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Check the spelling and grammar of the website |  |  | Passed
2 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Check the font, text color and style |  |  | Passed
3 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Hover over every fields |  |  | Passed
4 |  |  |  | Verifying all the text box , Calour, fornt, Style | All Text Fields should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/registered_companies 2. Verifying all the text box , Calour, fornt, Style |  |  | Passed
5 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Check alignment of the fields |  |  | Passed
1 | Admin Panel | UI Testing | Registered Companies | Checking spelling or grammatical mistakes | Found spelling or grammatical mistakes | Not found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/registered_companies 2. Check the spelling and grammar of the website | Alphabetical Mistake |  | Failed
2 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/registered_companies 2. Check the font, text color and style |  |  | Passed
3 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/registered_companies 2. Hover over every fields |  |  | Passed
4 |  |  |  | Checking alignment of the fields | Not Proper alignment of the fields should be present | Not Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/registered_companies 2. Check alignment of the fields | Alignment |  | Failed
5 |  |  |  | Verifying all the Calour, fornt, Style | All Text Fields should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/registered_companies 2. Verifying all the Calour, fornt, Style |  |  | Passed
|  |  |  | Improvement Scopes | 1. In CL-42, Si-01__There Was a Grammatical Mistake, Provide a screen Short. The word should start by an Capital Word. 2.In CL-45, Si-04__ There was an alignment mistake, Provide a screen short. The text should be allined | Please Check this Screen Short, (Marked Places) | Text Line and text boxes are not Allined
Enlisted Users With Permission Mode
1 | Admin Panel | UI Testing | Enlisted Users With Permission Mode | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Check the spelling and grammar of the pages |  |  | Passed
2 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Check the font, text color and style |  |  | Passed
3 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Hover over every fields |  |  | Passed
4 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Check alignment of the fields |  |  | Passed
1 | Admin Panel | UI Testing | User History | Checking spelling or grammatical mistakes | Found spelling or grammatical mistakes | Not Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Check the spelling and grammar of the Pages | Alphabetical Mistake |  | Failed
2 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Check the font, text color and style |  |  | Passed
3 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Hover over every fields |  |  | Passed
4 |  |  |  | Checking alignment of the fields | Not Proper alignment of the fields should be present | Not Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Check alignment of the fields | Alignment |  | Failed
5 |  |  |  | Verifying all the Calour, fornt, Style | All Text Fields should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Verifying all the Calour, fornt, Style |  |  | Passed
|  |  |  | Improvement Scopes | 1. In CL-64, Si-01__There Was a Grammatical Mistake, Provide a screen Short. The word should start by an Capital Word. 2.In CL-67, Si-04__ There was an alignment mistake, Provide a screen shorts In a Folder. The text with select box should be allined | Please Check this Screen Short (Start From:- Test Farmer TO END)
Request For Account Registration
1 | Admin Panel | UI Testing | Request For Account Registration | Did Not Work |  |  |  |  | Account Registration | Failed | Passed
Registered Farmers
1 | Admin Panel | UI Testing | All Registered Farmers | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Check the spelling and grammar of the website |  |  | Passed
2 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Check the font, text color and style |  |  | Passed
3 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Hover over every fields |  |  | Passed
4 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Check alignment of the fields |  |  | Passed
1 | Admin Panel | UI Testing | Registered Farmers | Checking spelling or grammatical mistakes | Found spelling or grammatical mistakes | Not Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Check the spelling and grammar of the Pages | Alphabetical Mistake |  | Failed
2 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Check the font, text color and style |  |  | Passed
3 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Hover over every fields |  |  | Passed
4 |  |  |  | Checking alignment of the fields | Not Proper alignment of the fields should be present | Not Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Check alignment of the fields | Alignment |  | Failed
5 |  |  |  | Verifying all the Calour, fornt, Style | All Text Fields should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Verifying all the Calour, fornt, Style |  |  | Passed
|  |  |  | Improvement Scopes | 1. In CL-98, Si-01__There Was a Grammatical Mistake, Provide a screen Short. The word should start by an Capital Word. 2.In CL-101, Si-04__ There was an alignment mistake, Provide a screen shorts In a Folder. The text with select box should be allined | Please Check this Screen Short
Farm Management- Creste / View Farmas
1 | Admin Panel | UI Testing | Total Farms | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Check the spelling and grammar of the website |  |  | Passed
2 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Check the font, text color and style |  |  | Passed
3 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Hover over every fields |  |  | Passed
4 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Check alignment of the fields |  |  | Passed
1 | Admin Panel | UI Testing | Farm Management - Create / view farms | Checking spelling or grammatical mistakes | Found spelling or grammatical mistakes | Not Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Check the spelling and grammar of the Pages | Alphabetical Mistake |  | Failed
2 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Check the font, text color and style |  |  | Passed
3 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Hover over every fields |  |  | Passed
4 |  |  |  | Checking alignment of the fields | Not Proper alignment of the fields should be present | Not Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Check alignment of the fields | Alignment |  | Failed
5 |  |  |  | Verifying all the Calour, fornt, Style | All Text Fields should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Verifying all the Calour, fornt, Style |  |  | Passed
|  |  |  | Improvement Scopes | 1. In CL-119, Si-01__There Was a Grammatical Mistake, Provide a screen Short. The word should start by an Capital Word. 2.In CL-122, Si-04__ There was an alignment mistake, Provide a screen shorts In a Folder. The text with select box should be allined | Please Check this Screen Short
Total Animal
1 | Admin Panel | UI Testing | Total Animal | Checking spelling or grammatical mistakes | No spelling or grammatical mistakes | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Check the spelling and grammar of the website |  |  | Passed
2 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Check the font, text color and style |  |  | Passed
3 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Hover over every fields |  |  | Passed
4 |  |  |  | Checking alignment of the fields | Proper alignment of the fields should be present | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/dashboard 2. Check alignment of the fields |  |  | Passed
1 | Admin Panel | UI Testing | Registered Cattle | Checking spelling or grammatical mistakes | Found spelling or grammatical mistakes | Not Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Check the spelling and grammar of the Pages | Alphabetical Mistake |  | Failed
2 |  |  |  | Verifying the font, text color and style | Should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Check the font, text color and style |  |  | Passed
3 |  |  |  | Checking by hovering over the fields | A text should appear over the fields | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Hover over every fields |  |  | Passed
4 |  |  |  | Checking alignment of the fields | Not Proper alignment of the fields should be present | Not Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Check alignment of the fields | Alignment |  | Failed
5 |  |  |  | Verifying all the Calour, fornt, Style | All Text Fields should be as per the requirement | Found as per expectation | N/A | 1. Goto the URL https://insurecow.xyz/superAdmin/history 2. Verifying all the Calour, fornt, Style |  |  | Passed
|  |  |  | Improvement Scopes | 1. In CL-140, Si-01__There Was a Grammatical Mistake, Provide a screen Short. The word should start by an Capital Word. 2.In CL-143, Si-04__ There was an alignment mistake, Provide a screen shorts In a Folder. The text with select box should be allined | Please Check this Screen Short